## One Time Cost
UNIT 2: Systems Planning ¦ PLANNING ESTIMATES (PHP)
BREAKDOWN OF ONE TIME COST WORKSHEET
Assumed project development duration: 3 MONTHS (part-time project fees)
A. Development Cost
BREAKDOWN OF ONE TIME COST WORKSHEET
| Description | Fee/Month |  | Mo. | Sub_Total
[7 empty] | A. Development Cost |  | 107000
| System Analyst (PT) | 10000 |  | 3 | 30000
[7 empty] | B. User Training |  | 4000
| Programmer (PT) | 20000 |  | 3 | 60000
[7 empty] | C. Additional Hardware/Software |  | 3500
| Encoder (PT) | 5000 |  | 1 | 5000
| Research / QA (PT) | 6000 |  | 2 | 12000
[7 empty] | TOTAL ONE TIME COST |  | 114500
| TOTAL |  |  |  | 107000
Total One Time Cost = Total Development Cost + Total User Training + Total Additional Hardware/Software
B. User Training
| Description |  | Honoraria/day |  |  | Sub_Total
| User Training (2 days) |  | 1500 |  |  | 3000
| Training Kit |  | 1000 |  |  | 1000
RECURRING COST
| TOTAL |  |  |  |  | 4000
[7 empty] | Description | Rate (PHP) |  | Annually
[7 empty] | Software Maintenance | 750 |  | 9000
C. ADDITIONAL HARDWARE/SOFTWARE
[7 empty] | Cloud Database + Storage | 1625 |  | 19500
[7 empty] | Static Frontend Hosting | 0 |  | 0
| Description |  | Unit Cost |  |  | Sub_Total
[7 empty] | Incremental Communication | 200 |  | 2400
| Cloud Database Setup |  | 1000 |  |  | 1000
[7 empty] | Domain Renewal (year) | 900 |  | 900
| External Drive |  | 2500 |  |  | 2500
[7 empty] | Software License Renewal | 0 |  | 0
| Open-source Tools / Free SSL |  | 0 |  |  | 0
[7 empty] | TOTAL |  |  | 31800
| TOTAL |  |  |  |  | 3500
PHP EST.
Total One Time Cost = Total Development Cost + Total User Training + Total Additional Hardware/Software
All financial figures are planning estimates in PHP, not actual company expenses. Maintenance, hosting and communication rates are monthly; renewals are annual. Free or bundled items are explicitly shown as 0.00. See Planning Basis for assumptions and sources.
IT303: SYSTEMS ANALYSIS AND DESIGN | [10 empty] | 1
Note on D15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D19: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F19: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D20: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F20: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on E29: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on E30: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on K36: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on K40: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on K42: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on E43: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on K44: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on E45: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on K46: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on E47: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.

## Cost Explanation
UNIT 2: Systems Planning ¦ PLANNING ESTIMATES (PHP)
| Training Kit | 1000 | 1000 | Description | Rate (PHP) | Annually
| TOTAL |  | 4000 | Software Maintenance | 750 | 9000
|  |  |  | Cloud Database + Storage | 1625 | 19500
|  |  |  | Static Frontend Hosting | 0 | 0
C. ADDITIONAL HARDWARE/SOFTWARE
|  |  |  | Incremental Communication | 200 | 2400
|  |  |  | Domain Renewal (year) | 900 | 900
| Description | Unit Cost | Sub_Total
|  |  |  | Software License Renewal | 0 | 0
| Cloud Database Setup | 1000 | 1000
|  |  |  | TOTAL |  | 31800
| External Drive | 2500 | 2500
| Open-source Tools / Free SSL | 0 | 0
| TOTAL |  | 3500
Total One Time Cost = Total Development Cost + Total User Training + Total Additional Hardware/Software
PHP EST.
The estimated one-time investment is PHP 114,500.00: development PHP 107,000.00, user training PHP 4,000.00, and deployment/backup hardware PHP 3,500.00. Estimated annual recurring cost is PHP 31,800.00. These figures form a planning scenario and are not actual company spending or approved vendor quotations.
The green company monitoring table records 758 units across 26 equipment categories. It identifies 19 round shovels, 75 GI pipes and 369 swivel clamps under “Missing or No Report,” totaling 463 units. These are reconciliation gaps; the table does not establish confirmed financial losses.
Estimated annual operational value is PHP 80,290.00, comprising PHP 4,690.00 in supplies cash savings and PHP 75,600.00 in released staff capacity. The capacity value is not payroll savings. Supplies savings alone do not cover the PHP 31,800.00 yearly running cost; the net cash requirement remains PHP 27,110.00 per year.
IT303: SYSTEMS ANALYSIS AND DESIGN | [6 empty] | 2

## Tangible Benefits
UNIT 2: Systems Planning ¦ PLANNING ESTIMATES (PHP)
• Benefit
Breakdown of Tangible Benefit Worksheet
A. SUPPLIES COST
| EXISTING SYSTEM | [5 empty] | PROPOSED SYSTEM
| Description | Qty |  | Price/Qty |  | Sub_Total | Description | Qty |  | Price/Qty |  |  | Sub_Total
| Folders (bundle) | 4 |  | 150 |  | 600 | Folders (bundle) | 2 |  | 150 |  |  | 300
| Ballpen (box) | 3 |  | 150 |  | 450 | Ballpen (box) | 2 |  | 150 |  |  | 300
| Bond Papers (ream) | 12 |  | 250 |  | 3000 | Bond Papers (ream) | 4 |  | 250 |  |  | 1000
| Carbon Paper (pack) | 1 |  | 150 |  | 150 | Record Book (pc) | 2 |  | 80 |  |  | 160
| Record Book (pc) | 6 |  | 80 |  | 480 | USB (piece) | 0 |  | 400 |  |  | 0
| Vouchers (pad) | 12 |  | 60 |  | 720 | Ink (bottle) | 3 |  | 350 |  |  | 1050
| Ink (bottle) | 6 |  | 350 |  | 2100
| TOTAL |  |  |  |  | 7500 | TOTAL | [5 empty] | 2810
Supplies Cost Reduction = Total Supplies of the Existing System − Total Supplies of the Proposed System
| Supplies Cost Reduction | [10 empty] | 4690
B. LABOR AND PRODUCTIVITY VALUE
| EXISTING SYSTEM | [5 empty] | PROPOSED SYSTEM
| Activity |  | Allocated Cost/ Month |  | Annual |  | Activity |  | Allocated Cost/ Month |  | Annual
| Inventory monitoring |  | 6000 |  | 72000 |  | Inventory monitoring |  | 3000 |  | 36000
| Report preparation |  | 2400 |  | 28800 |  | Report preparation |  | 900 |  | 10800
| Reconciliation / follow-up |  | 3600 |  | 43200 |  | Reconciliation / follow-up |  | 1800 |  | 21600
| TOTAL |  |  |  | 144000 |  | TOTAL |  |  |  | 68400
Productivity Value = Existing Allocated Labor Cost − Proposed Allocated Labor Cost
| Labor Productivity Value | [10 empty] | 75600
Total Annual Tangible Value = Productivity Value + Supplies Cash Savings
| Total Annual Tangible Value | [10 empty] | 80290
Estimated annual supplies spending falls from PHP 7,500.00 to PHP 2,810.00, a potential cash saving of PHP 4,690.00. Allocated labor falls from PHP 144,000.00 to PHP 68,400.00, releasing capacity valued at PHP 75,600.00 per year. Combined tangible value is PHP 80,290.00; no salary or headcount reduction is assumed.
No equipment-loss or recovery saving is credited (PHP 0.00). The 463 missing or unreported units remain a reconciliation concern, not confirmed losses. A USB purchase is unnecessary in this scenario because cloud reporting and the separately budgeted backup drive are available; its subtotal is PHP 0.00.
IT303: SYSTEMS ANALYSIS AND DESIGN | [13 empty] | 3
Note on D12: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F12: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on L12: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on N12: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D13: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F13: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on L13: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on N13: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D14: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F14: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on L14: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on N14: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on L15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on N15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D16: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F16: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on L16: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on N16: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on L17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on N17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on D18: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on F18: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.

## Company Inventory
HAND TOOLS AND OTHERS MONITORING
ITEM NO. | POWER TOOLS | QTY. | NEED TO COMPLY | MISSING OR NO REPORT
1 | SHOVEL (PALA, LAPAD) | 19 | — | —
2 | SHOVEL (PALA, BILOG) | 23 | 42 | 19
3 | BARETA | 13 | — | —
4 | ITAK | 4 | — | —
5 | PIKO | 4 | — | —
6 | PLASTIC DRUM 200L | 14 | — | —
7 | IBC WATER TANK 1000L | 5 | — | —
8 | WHEEL BARROW | 4 | — | —
9 | OXYGEN TANK | 3 | — | —
10 | GAS TANK | 5 | — | —
11 | ELECTRIC KETTLE | 2 | — | —
12 | EXTENSION | 10 | — | —
13 | DOUBLE BURNER STOVE | 8 | — | —
14 | LABABO | 5 | — | —
15 | MASO | 4 | — | —
16 | GARDEN HOSE | 5 | — | —
17 | GI PIPES | 225 | 300 | 75
18 | BASE JACK | 27 | — | —
19 | U-JACK | 56 | — | —
20 | BUCKETS | 39 | — | —
21 | CATWALK FLATFORM SCAFFOLDING | 33 | — | —
22 | H-FRAME SCAFFOLDING | 64 | — | —
23 | BRACES SCAFFOLDING | 41 | — | —
24 | WATER-PUMP | 2 | — | —
25 | GARDEN SPRINKLER | 2 | — | —
26 | SWIVEL CLAMP | 141 | 510 | 369
SOURCE CHECK: 26 populated categories; 758 recorded units; 463 missing or unreported units.
A dash means not reported in the source, not zero. Only three categories have supplied requirements and gaps. The 463 units are not confirmed physical losses. “CATWALK FLATFORM SCAFFOLDING” preserves the source spelling; unused row 27 is omitted.
Source: user-supplied green “HAND TOOLS AND OTHERS MONITORING” image. Application records are demonstration data and are excluded.
COMPANY DATA SOURCE: GREEN INVENTORY TABLE ONLY |  |  |  |  | 4

## Input Details
PLANNING BASIS — EDITABLE ESTIMATES (PHP)
These financial values and task timings are illustrative estimates, not actual company expenses. Only the green inventory quantities are company data. A three-month build is assumed; project fees cover part-time services.
Supporting input | Estimate | Unit / basis
Training duration | 2 | days
Cloud deployment setup quantity | 1 | setup service
External backup drive quantity | 1 | one drive
Open-source / SSL package quantity | 1 | free package
Planning exchange rate | 65 | PHP per USD
Hosted backend subscription | 25 | USD per month [S1]
Administrative time valuation | 150 | PHP per person-hour
Existing inventory-monitoring time | 40 | person-hours per month
Existing report-preparation time | 16 | person-hours per month
Existing reconciliation / follow-up time | 24 | person-hours per month
Proposed inventory-monitoring time | 20 | person-hours per month
Proposed report-preparation time | 6 | person-hours per month
Proposed reconciliation / follow-up time | 12 | person-hours per month
Cost boundaries: coding/testing is covered by the development retainers; PHP 1,000 setup covers account provisioning and deployment checks. The backup drive is a separate offline export copy. Hosted database storage and bundled database backups are paid once; frontend hosting, open-source licenses and SSL add no separate fee.
Labor basis: estimated monthly task time falls from 80 to 38 person-hours. The 42 hours released each month equal 504 hours/year; at PHP 150/hour, productivity value is PHP 75,600/year. This does not reduce payroll. Supplies savings are PHP 4,690/year; after PHP 31,800 recurring costs, net cash impact is negative PHP 27,110/year.
BENCHMARKS AND SOURCES — CHECKED 24 OCTOBER 2026
[S1] Supabase Pro: USD 25/month starting price, within stated quotas. https://supabase.com/pricing
[S2] Cloudflare Pages Free: static hosting limits apply. https://developers.cloudflare.com/pages/platform/limits/
[S3] Registrar: no-markup domain pricing and included SSL. PHP 900 is an allowance. https://www.cloudflare.com/domains/
[S4] Philippine wage context only; company wages are unknown. https://nwpc.dole.gov.ph/ncr/
[S5] Official FX reference. PHP 65/USD is a rounded planning conversion. https://www.bsp.gov.ph/SitePages/Statistics/exchangerate.aspx
Other rates, supplies quantities, hardware allowance and time reductions are analyst estimates, not quotations. Training includes a basic two-day orientation; any additional paid participant overtime needs a revised budget. Confirm taxes, actual usage and remaining development scope before spending.
PLANNING ESTIMATES; COMPANY SOURCE: GREEN INVENTORY TABLE ONLY |  |  | 5
Note on C7: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C8: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C9: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C10: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C11: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C12: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C13: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C14: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C15: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C16: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C17: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C18: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.
Note on C19: Editable planning estimate, not an actual company bill or wage. Replace with a verified quote or measured value when available. Zero means an explicit free/bundled/not-required item in this scenario.